## Pre-bid
Tender Enquiry No.: TPCODL/P&S/1000000928/24-25
Project Name - Construction of Residential Training Center at Puri, TPCODL
Pre-bid Queries List
Sl No. | Page No. | Clause No. | Topic | Description | Only Comments | TPCODL Response
1 | SCC (P- 1 of 5) | 4 | Terms of Payment | Terms of Payment for Contract Works: (i) Monthly running bill shall be paid based on actual completion of work at site duly certified by Engineer in charge. (ii) EMD: Rs 09 Lakhs in the form of Bank Guarantee as per approved format or through NEFT to TPCODL Bank account. EMD shall be released to unsuccessful bidders after finalization of Contractor whereas EMD of successful bidder shall be released after submission of CPBG. iii) CPBG: Contractor shall submit a Contract performance bank Guarantee @5% of the Contract Value valid till completion of the Defect liability Period. CPBG shall be submitted within 15 days from the date of award of work as per approved format. iv) ADBG - 10% of contract price shall be paid as advance against submission of Bank Guarantee of equivalent amount valid till completion of work and on completion of the following: • Mobilisation of manpower and machineries, tools. • Kick off meeting. • Submission of Schedule of Project completion, as agreed. Advances shall be recovered @15% of RA bills starting from first RA and shall be recovered fully by the time 70% of the work is complete. Advance Bank Guarantee value shall be reduced at regular intervals after recovery of advances from the running account bills. v) Income tax and any other statutory recoveries as applicable shall be recovered from Contractor monthly running bills and TDS certificate for the deductions shall be furnished. All payments are subject to signing of Contract Agreement and submission of an unconditional Performance bank guarantee as mentioned in item No (ii) above. | (ii) We request you to waive off the EMD. (iii) We request you to waive off the Performance Bank Guarantee. iv) We request, paid an interest free Mobilization advance @10% at the time of contract to the contractor & the same shall be deducted from contractors RA bill in pro-rata percentage basis up to completion of 85% of Bill value. | Tender Clause will remain unchanged.
2 | SCC (P- 2 of 5) | 5 | Due Dates of Payments | Payment shall be released within 15 days from the date of receipt of certified RA bill and within 30 days from the date of submission of final certified bill. | 70% payment of R/A bills shall be made within 10 days from the date of submission of bill to the Client and balance 30% shall be made within 21 days from the date of submission of bill to the Client. | Tender Clause will remain unchanged.
3 | SCC (P- 3 of 5) | 7 | Completion Schedule | Entire job has to be completed within 06 months from the date of award of contract and handover of site. Detail completion micro schedule L2 to be approved from owner/Project Manager before start of work, same to be reviewed every month. | We request the completion period shall be fixed 8 Months of the project. | Tender Clause will remain unchanged except in force majure conditions.
4 | SCC (P- 3 of 5) | 12 | Water For Construction | Construction water will be arranged by Contractor at its own expense. | We request Water shall be supply by Client free of cost at one point inside the premises & further distribution will be Contractors scope. If bidder provides water, the cost should be reimbursed to us separately on actuals. | Tender Clause will remain unchanged.
5 | SCC (P- 3 of 5) | 13 | Construction Power Supply | Construction power will be arranged by contractor at its own expense. | We request Electricity shall be supply by Client free of cost at one point inside the premises & further distribution will be Contractors scope. | Tender Clause will remain unchanged.
6 | GCC (P-19 of 98) | 13 | Liquidated Damages | For delay of each week and part thereof, from the execution of work schedule specified in the milestone, 1% of the contract value corresponding to the unexecuted work of the milestone, subject to a maximum of 10% of the total contract value of that milestone shall be levied. | If any delay occurs from the Client end for drawings, decision, site clearance then, no LD will be imposed. We request you to consider Liquidated Damages at the rate of 0.5% of balance work per week and maximum upto 5% of the balance contract price. | Tender Clause will remain unchanged.
7 | GCC (P-19 of 98) | 8 | Security Cum Performance Deposit | Associates shall submit within 15 days from the effective date of issue of PO/RC, Security cum Performance Bank Guarantee (SPBG) in the format as per Annexure B of this document from banks acceptable to TPCODL for: (a) 5% of the PO value if purchase order value is more than Rs 5 Crores. (b) 10% of the PO value if purchase order value is less than Rs 5 Crores. This shall remain valid till the end of the Guarantee Period of contract, plus one month. (c) 5% of the RC value in case of Rate Contract. This shall remain valid till the Guarantee period plus one month. | We request you to waive off the Performance Bank Guarantee. Cash Retention from RA Bills shall be 5% (five percent) of bill value; 50% of the retention amount shall be released upon completion of work and balance 50% of the retention amount shall be released on expiry of defect liability period, i.e., 12 (twelve) months from the date of virtual completion of work. | This will be applicable as mentioned in Annexure-A spesicial conditions of cpontract attached in the tender document.
8 | SCC (P-4 of 5) | 15(a) | Services and facility by owner | The Contractor shall be responsible for all costs associated with rent, royalties, cess, and other charges for materials, as well as all applicable taxes, including GST, ferry tolls, conveyance charges, and any costs related to land and buildings (including temporary structures) necessary for the collection of materials, storage, housing of staff, or other work-related purposes. Any construction must be carried out only after obtaining written permission from the Engineer- in-Charge. Upon completion of the work, all such constructions must be demolished, and debris must be removed. The site must be restored to its original condition at no additional cost. | We request Labour Cess to be in Client scope. | Tender Clause will remain unchanged.
9 | SCC (P-4 of 5) | 15(e) |  | All fees and dues levied by Municipal, Canal or Water Supply Authorities are to be borne by the Contractor. | Any clearance required from the Govt. Authority to be taken by the Client. | Tender Clause will remain unchanged.
10 | Data Sheet For Civil And Structural Works (P-8 of 9) | 4(g) | Disposal | Excavation at all depths (Unless otherwise mentioned in schedule), stacking usable and disposal of surface earth and materials from site as directed including submitting receipt of disposed material at approved municipal dumping ground. | Dumping yard to be provided by the Client. | Tender Clause will remain unchanged.
11 |  |  | Secured Advance |  | Secured advance against Steel & Cement to be paid 100% of invoice value. | Not applicable
12 |  |  | Excavation |  | Dewatering sea water and any soil protection work will not be in bidder scope. | Will be scope of bidder.