## Sheet1
TPCODL Format for prebid Query / Clarification / Deviation (QCD)
Tender NIT No. TPCODL/P&S/2025-26/ 1000002493
Pre Bid Queries Response | [5 empty] | 19.05.2025
Tender description: Strengthening of electrical infrastructure in elephant corridor & movement area in TPCODL on Turnkey basis (TPCODL/P&S/2025-26/1000002493)
S No | Clause No | Page No | Tender Description | Bidder's Query / Clarification | Bidder's Justification | TPCODL Response
1 | BOQ |  |  | GIS marking of Pole is not in the BOQ.Clarify wheather it is required or not. If Required it may be added to BOQ | GIS marking of Pole is not in the BOQ.Clarify wheather it is required or not. If Required it may be added to BOQ | GIS marking of pole is required . Which will be done as per direction of the Project In-Charge/ Site Engineer. The items mentioned in erection BoQ sl no 18 & 19 is inclusive of GIS Numbering & Zebra striping. Due to above change in Items Description in erection BOQ at Sl 18 & 19, the revised "Schedule of Items (Annexure-I)" is attched separatrely for necessary quotation. Bidders are requested to submit the tender as per revised Price Schedule. Price bid received in any other format from a bidder shall be out-rightly rejected by TPCODL.
2 | 7.1.7. | 15-16 | (B) Terms of Payment: Payment shall be made in the following stages, A) 80% (Eighty Percent) of contract price along with taxes and duties shall be paid progressively in monthly basis for each completed items of work against installation certified by the Order manager. B) Balance 20% (Twenty percent) of contract price shall be paid after completion of all works, envisaged under this package including Handing over and Taking Over, return of dismantled materials, clearance of Electrical Inspection, compliance thereof, Forest Dept. and reconciliation etc and others documentations as required by the Order manager. | There is No Payment against Supply of Materials. Requesting to consider atleat 70% Payment against Supply of Materials post delivery at Site duely inspected. | Payment Against Materials Ensure these 1-No Blockage of Big Capitals for Procurement of Large Scale Materials Like Cable,Conductors and Poles. 2-Procure quality materials in bulk and at competitive rates. 3-Ensure uninterrupted supply and availability of items at site. 4-Accelerate project timelines due to ready material availability In earlier Elephant Corridor projects executed under TPWODL (Ref: RC No. 6200002840 and RC No. 6200002862), there was provision for payment against material supply was included as part of the contractual payment structure. | Tender clause stand.
3 | 7.1.9 | 16 | Submittals Required After Award Of Contract : The BA shall provide documents to the EIC i.e. Outline program of survey, production, inspection, testing, delivery, erection, pre-commissioning and commissioning in chart form to the Order Manager. The Drawings and Guaranteed Technical particulars (GTP), Type test report, QAP of all bought out material of specified in the tender shall be submitted prior to inspection. The time line to submit the GTP & drawing of materials should be within 15 days | After Issue of Order Wheather the Survey Drawings has to be Signed from Forest Department Officials. If yes then whose responsibility is this to get these Documents signed. And Also Forest Clearance is needed or Not. | As this is a Elephant Corridor Project Generally Survey Drawings and Permission has to be get from Forest Department. | The locations mentioned in tender are already been jointly surveyed by Forest Dept & TPCODL . The BA will conduct actual survey jointly with Concerned Section Manager & Project Engineer and signed before execution of work .
4 | 7.1.10 | 16 | Inspection: i) PRE DISPATCH INSPECTION – The BA shall give advance notice for testing of all bought out materials as per approved make. The required DI shall be issued after which the BA shall lift the materials. The contractor shall ensure that all the inspected materials along with intact seal at site and the same will be again cross checked and certified in the presence of Order manager. ii) POST DELIVERY & WORK INSPECTION – The Order Manger will inspect all required materials delivered at work site and will inspect the execution of work from time to time up to final completion. The work shall be verified by the owner’s representative and by DMU Gridco. However, the quality of the materials will be inspected by the Electrical Inspector regularly prior to installation. iii) INSPECTION OF COMPLETED WORK – The work after due completion under the supervision of the Order manager shall be inspect with the competent authority of Electrical Inspectorate, Govt. of Odisha and by DMU Gridco. All arrangement for this inspection shall be the responsibility of the BA. The statutory fees (if any) regarding Electrical Inspection for entire scope of work shall be deposited by BA. However, such Inspection and Testing shall not relieve Contractor of his obligation to execute the contract by letter of spirit. Any defects pointed out by the Electrical Inspector (if any), shall be corrected or attended by the BA at his own cost. | For Raising a Running Bill is it requred to do Electrical Inspection. | For RA Bill what the Documents required to certify from whom Is there anything to be certify from Forest department? | To raise a Running bill, location wise Electrical inspection report from Govt is required
5 | BOQ |  |  | There is no Items for Tree Cutting.Wheather it is required or Not. If required whose scope is to get the Permission for Tree Cutting. | There is no Items for Tree Cutting.Wheather it is required or Not. If required whose scope is to get the Permission for Tree Cutting. | Tree cutting/ triming and obtain permission (if any) for same is part of the contractor scope.
6 | 1.1 | 6 | Scope of work | The total Package estimated value of Rs.13.35 Crore will be difficult to complete within 8 months schedule completion considering the complexity of the project. It is therefore requested to split the package as per individual electric division like earlier Elephant Corridor Tender which will enable more local MSME bidders like us to participate ensuring competitive bidding. | Previous Elephant Corridor Tender was as per Division with provision of Joint Venture. We participated and successfully executed 2 Nos Packages namely TPCODL Nayagrh & TPSODL Rayagada Packages. | It will be governed by the tender Evaluation criteria clause.
7 | 1.7 | 7 &8 | Qualification Criteria | Experience in Successsful completion of Elephant Corrdor Works / Packages may please be considered irrespective of other Qualifying Criteria. | We have successfully completed 2 Nos Elephant Corridor Packages for Tata Power Discoms | Tender conditions stand.
8 | 1.1 | 6 | Scope of work | The Package may kindly be split as per 5 Forest Zones or 3 Electrical Divisions considering the complexity of the work. Moreover, Division wise package will help in completing the package within schedule. | This tyoe of work requires lot of coordination with DISCOM, Forest and other Govt, Departments. Moreover, ensuing monsoon season may also be taken into consideration. Hence it is requested to split the package which will surely add to efficiency of the work. | It will be governed by the tender Evaluation criteria clause.
9 | 1.1 | 6 | Scope of work | The Package may kindly be split as per 5 Forest Zones or 3 Electrical Divisions which will facilitate schedule completion of 8 months as such type of work requires lot of coordination with Discom, Forest & other statutory bodies. | Package with Lesser scope and value and Division specific will surely add to efficiency of timely project completion. | It will be governed by the tender Evaluation criteria clause.
10 | 1.7 | 7 | Qualification Criteria | The bidder must have successfully Constructed at least 40 Ckt. Kms of 33 kV / 11 kV/ LT Overhead line on EPC Contract / Turnkey Contract basis, in any utility/companies during Last Five Years preceding to the date of NIT. | We are registered global RC contractor of TPCODL and have huge erection & stringing experience including stringing of Covered Conductor in Dhenkanal zone but not on turnkey basis. It is requested to consider our technical qualification especially taking into consideration our MSME status and our long association with TP Odisha Discoms. | Tender conditions stand.